## Sheet1
Sr No | Topic | Meeting With | Proposed Date | Expected Hour | Tentative time
1 | Function Knowledge | Cedric and Sandra | 2018-01-29 | 3 | 09:00 to 12:00
2 | Call handling and CR Request handling | Support by Gyandeep | 2018-01-29 | 2 | 13:00 to 15:00
3 | Technical Understanding (WANT) | Cedric and Sandra | 2018-01-29 | 2 | 15:00 to 17:00
4 | Change Request Overview and Deployment discussion | Cedric | 2018-01-30 | 1 | 09:00 to 10:00
5 | Technical Meeting | Sandra and Danny | 2018-01-30 | 1.5 | 10:00 to 11:30
6 | Call handling and CR Request handling | Support by Gyandeep | 2018-01-30 | 2 | 13:00 to 15:00
7 | Technical Understanding (FRET) | Cedric and Sandra | 2018-01-30 | 2 | 15:00 to 17:00
8 | Server Migration and OKTA Validation (Development) | Cedric, Sachin and Data Center Team | 2018-01-31 | 3 | 09:00 to 12:00
9 | Call handling and CR Request handling | Support by Gyandeep | 2018-01-31 | 2 | 13:00 to 15:00
10 | Technical Understanding (FRET) | Cedric and Sandra | 2018-01-31 | 2 | 15:00 to 17:00
11 | Server Migration and OKTA Validation (Staging) | Cedric, Sachin and Data Center Team | 2018-02-01 | 3 | 09:00 to 12:00
12 | Call handling and CR Request handling | Support by Gyandeep | 2018-02-01 | 2 | 13:00 to 15:00
13 | Technical Understanding (DISWANT) | Cedric and Sandra | 2018-02-01 | 2 | 15:00 to 17:00
14 | Server Migration and OKTA Validation (Production) | Cedric, Sachin and Data Centre Team | 2018-02-02 | 3 | 09:00 to 12:00
15 | Call handling and CR Request handling | Support by Gyandeep | 2018-02-02 | 2 | 13:00 to 15:00
16 | Technical Understanding (DisWant) | Cedric and Sandra | 2018-02-02 | 2 | 15:00 to 17:00
17 | Server Migration and OKTA Validation (Web Service) | Cedric and Data Center Team | 2018-02-05 | 3 | 09:00 to 12:00
18 | Call handling and CR Request handling | Support by Gyandeep | 2018-02-05 | 2 | 13:00 to 15:00
19 | Technical Understanding (Web Service) | Cedric | 2018-02-05 | 2 | 15:00 to 17:00
20 | Technical Understanding (Windows Service + Credit Note Service) | Cedric and Sandra | 2018-02-06 | 2 | 09:00 to 11:00
21 | Call handling and CR Request handling | Support by Gyandeep | 2018-02-06 | 2 | 13:00 to 15:00
22 | Call handling discussion | Cedric and Sandra | 2018-02-06 | 1 | 15:00 to 16:00
23 | Deployment of CR and Testing | Cedric | 2018-02-06 | 1 | 16:00 to 17:00
24 | Business Meeting for TESS application | Cedric, Sachin (Over Phone ) and Danny | 2018-02-07 | 1.5 | 09:00 to 10:30
25 | Meeting with ERP team for Credit flow implementation | Cedric and Data Centre Team | 2018-02-07 | 1.5 | 10:30 to 12:00
26 | Call handling and CR Request handling | Support by Gyandeep | 2018-02-07 | 2 | 13:00 to 15:00
27 | Technical Documentation implementation | Cedric | 2018-02-07 | 1.5 | 15:00 to 16:30
28 | Call handling and CR Request handling | Support by Gyandeep | 2018-02-08 | 3 | 09:00 to 12:00
29 | GIT Discussion | Cedric, Ronny and Ben | 2018-02-08 | 1 | 13:00 to 14:00
30 | Call handling and CR Request handling | Support by Gyandeep | 2018-02-08 | 1.5 | 14:00 to 15:30
31 | Business Meeting for TESS application | Sandra | 2018-02-08 | 1 | 15:30 to 16:30
32 | Server Migration Validation and Testing | Cedric | 2018-02-09 | 3 | 09:00 to 12:00
33 | New CR Overview | Cedric and Sandra | 2018-02-09 | 2 | 13:00 to 15:00
34 | TESS application Doubt and concern | Cedric | 2018-02-09 | 2 | 15:00 to 17:00